# Project Zava – Project plan

Version 1.0 – plan baseline (Month 0) | Owner: Lynne Robbins, Project Lead

# 1. Purpose and scope

Project Zava replaces Contoso's legacy customer-service ticketing tools with one global customer-service platform covering case management, a shared knowledge base and a customer portal for Contoso's service centres. The rollout runs in three country waves so that each centre moves onto the platform with its own cut-over and hypercare period.

Wave 1: Brazil, São Paulo service centre (140 agents)

Wave 2: Germany (110 agents)

Wave 3: Japan (90 agents)

Out of scope: field service and the sales CRM. Both remain on their current systems and are not affected by the rollout.

# 2. Objectives and KPIs

Success is measured against the plan baseline (Month 0). The targets below are reported monthly to the steering committee.

| Objective | Baseline (Month 0) | Target |
| --- | --- | --- |
| First-contact resolution | 64% | 75% |
| Average handling time | Current average | 15% reduction |
| Customer satisfaction (CSAT) | 78% | 85% |
| Knowledge base | Separate local repositories | One knowledge base in 3 languages |
| Legacy tools | In use in all centres | Decommissioned by Month 9 |

# 3. Timeline and milestones

All timing is relative to the plan baseline (Month 0). Wave go-live dates can only change with steering committee approval.

| Milestone | Planned | Owner |
| --- | --- | --- |
| Design complete | Month 2 | Lynne Robbins |
| Data migration rehearsal | Month 3 | Megan Bowen |
| Agent training Brazil | Month 4 (2 weeks before go-live) | Isaiah Langer |
| Wave 1 go-live Brazil | End of Month 4 | Miriam Graham |
| Wave 2 go-live Germany | Month 6 | Country lead (to be named) |
| Wave 3 go-live Japan | Month 8 | Country lead (to be named) |
| Legacy decommissioning | Month 9 | Megan Bowen |

# 4. Workstreams

| Workstream | Lead | Scope |
| --- | --- | --- |
| IT & data migration | Megan Bowen | Platform configuration, migration of 1.2 million historical cases, integrations |
| Country deployment | Miriam Graham (Brazil) | Local processes, cut-over, hypercare |
| Training & change | Isaiah Langer | Agent training, knowledge articles, super-users |
| Project management | Lynne Robbins | Plan, RAID log, steering, budget |

Isaiah Langer joins the project next week and takes over the training and change workstream from that point.

# 5. Governance

Weekly project sync, organised by Megan Bowen and attended by all workstream leads.

Monthly steering committee chaired by Alex Wilber, Executive Sponsor (VP Customer Operations).

Decisions above USD 50k, and any change to a go-live date, require steering committee approval.

# 6. Budget

The approved budget is USD 2.4M, split as follows.

| Category | Amount (USD) |
| --- | --- |
| Licences | 0.9M |
| Implementation partner | 0.8M |
| Data migration | 0.3M |
| Training & change | 0.2M |
| Contingency | 0.2M |
| Total | 2.4M |

# 7. Key risks at plan time

| Risk | Impact | Mitigation | Owner |
| --- | --- | --- | --- |
| Data quality of historical cases | May delay migration | Early data profiling and cleansing; full migration rehearsal in Month 3 | Megan Bowen |
| Agent availability for training during peak season | Agents not ready at go-live | Schedule training in small groups; train super-users first | Isaiah Langer |
| Integration with the telephony system | Delayed or degraded go-live | Integration testing in the Month 3 rehearsal; vendor on standby | Megan Bowen |
| Portuguese knowledge-base translation | Incomplete content in Brazil at go-live | Prioritise top articles; native-speaker review by local super-users | Miriam Graham |
| Key-user dependency | Loss of process knowledge | Document processes; name a backup for each key user | Lynne Robbins |

# 8. Communication plan

Day-to-day coordination happens in the Teams group chat, while decisions, status and escalations are captured in the weekly sync and the monthly sponsor email so that there is a written record for the steering committee.

| Channel | Audience | Frequency |
| --- | --- | --- |
| Weekly project sync | All workstream leads | Weekly |
| Teams group chat "Project Zava core team" | Core team | Day-to-day |
| Status email to the sponsor | Alex Wilber | Monthly |
| Steering committee pack | Steering committee | 3 working days before each meeting |

# 9. Document control

| Item | Detail |
| --- | --- |
| Version | 1.0 |
| Status | Plan baseline (Month 0) |
| Owner | Lynne Robbins, Project Lead |
| Approver | Alex Wilber, Executive Sponsor (VP Customer Operations) |
| Next review | Month 1 steering committee |

Contoso Ltd – Internal use – fictitious demo content.